## Sheet1
Board of Commissioners of Public Lands
Fiscal Year 2021 - Planned Timber Sale Set-Up and Bidding
Project | Spring/Fall | Cutting |  |  |  | Sale | [5 empty] | Eco | Cutting | Field
Lead | Bid | Period | County | Legal Description | Acres | Number | Sale Common Name | General Harvesting Prescription | Status | Recon | Cruise | Plan | Plan | Set-up | Notes
Kevin | Spring 2021 | Dry Summer | Florence | T39N-R16E Sec 26, 35, T38N-R16E Sec 12 | 106 | TS-202103 | Goodman Grade Hardwoods | Northern hardwood marked selection thinning - pulp + sawlogs |  | X | X | X | X |  | Sample Mark
Kevin | Fall 2021 | Dry Summer | Forest | T36N-R15E Sec 1 | 259 | TS-202105 | Cavour North | Northern hardwood marked selection thinning - pulp + sawlogs
Joe | Spring 2021 | Dry Summer | Oneida | T37N-R13E Sec 12 | 19 | TS-202107 | Replacement Pine | Red Pine second thinning plus small Aspen Clearcuts |  | X |  |  |  |  | Already marked - just needs volume cruise
Joe | Spring 2021 | Dry Summer | Iron | T41N-R04E Sec 9 | 85 | TS-202102 | Springstead Aspen/red maple | Aspen clearcuts and Red Maple shelterwood thinnings
John | Spring 2021 | Dry Summer | Langlade | T34N-R12E Sec 3 | 6 | TS-202113 | Langlade Red Oak | Red Oak intermediate thinning | Permit sale for adjacent Logger | X
Joe | Fall 2021 | Frozen Only | Ashland | T43N-R10W Sec 26, 27, 35 | 90 | TS-201810 | Agustine Lake South 40 | Marked northern hardwoods | [6 empty] | Re-evaluate and set-up new
Kevin | Spring 2021 | Frozen Only | Forest | T37N-R14E Sec 8, 17, 19, 20 | 48 | TS-202101 | Peshtigo Frozen Pines | Red pine marked selection second thinning |  | X |  |  |  |  | Sample mark
Joe | Fall 2021 | Frozen Only | Iron | T42N-R02E Sec 3, T43N-R2E Sec 34 | 112 | TS-202002 | Moose Creek West | Northern hardwood marked selection thinning - mostly pulpwood | [6 empty] | Re-evaluate and set-up new
Kevin | Fall 2021 |  | Oneida | T37N-R11E Sec 9, 16 | 37 | TS-202109 | Hunting Camp Hardwoods | Northern hardwood marked selection thinning - shelterwood
John | Fall 2021 | Frozen Only | Price | T36N-R01W Sec 20,28,29 | 80 | TS-202006 | Needle Creek Red Maple | Red Maple shelterwood thinnings | [6 empty] | Re-evaluate and set-up new
John | Fall 2021 | Frozen Only | Price | T36N-R03E Sec 2 | 47 | TS-202106 | Scott Creek Aspen/Hardwoods | Aspen clearcuts, and red maple shelterwood thinnings
Kevin | Spring 2021 | Dry Summer | Florence | T38N-R10E Sec 16 | 9.6 | PS-202114 | Woods Creek Aspen | Aspen clearcut along with a Spruce/Fir streamside buffer thinning | Permit Sale - sold - Frank's | X | X | X | X | X
Kevin | Spring 2021 | Dry Summer | Oneida | T38N-R10E Sec 16 | 23 | PS-202111 | UWSP Thunder Lake 40 | Northern hardwood marked selection + aspen/fir cleacut | Permit Sale - sold - Great North | X | X | X | X | X
Kevin | Fall 2020 | Frozen Only | Ashland | T42N-R03W Sec 8, 17 | 100 | TS-202104 | Moose River Shelterwood | Northern hardwood marking | Sold - North Country
Kevin | Winter 2021 | Frozen Only | Forest | T41N-R14E Sec 35 | 40 | PS-202110 | Huff Creek Blowdown | Blowdown salvage hardwoods and aspen | Cutting Complete
Kevin | Winter 2021 | Frozen Only | Forest | T41N-R14E Sec 35 | 14 | PS-202112 | Huff Creek Blowdown - 2 | Aspen/Fir blowdown salvage | Cutting Complete
Kevin | Fall 2020 | Spring Breakup | Marinette | T34N-R18E Sec 34 | 80 | TS-202108 | Marinette Pine Pulwood | Jack pine, red pine, scub oak clearcut | Sold - Wild Rivers
|  | Total Sales: | 17 | Total Acres: | 1155.6
Spring Bid
Fall Bid
Sold/Complete